## Agile Project Plan Template
AGILE | MODUL 5 MACHINE LEARNING | [6 empty] | CHART
TOTAL TASKS | 14 |  | DURATION | 764 |  | Overall Progress
Completed | 14 |  | START | 2023-04-12
In progress | 0 |  | FINISH | 2023-11-12 |  | 100%
Not Started | 0
0%
NO | TASKS | DEV |  | START | FINISH | DURATION (MINUTE) | STATUS
1 | LOAD DATA | FREDERICK HUISAND SUTIRTO |  | 2023-04-12 | 2023-04-12 | 10 | Completed
2 | PREPROCESSING DATA | FREDERICK HUISAND SUTIRTO |  | 2023-04-12 | 2023-04-12 | 38 | Completed
3 | AUGMENTATION DATA | FREDERICK HUISAND SUTIRTO |  | 2023-04-12 | 2023-04-12 | 20 | Completed
4 | MODELLING WITH NO IMAGE AUGMENTATION | FREDERICK HUISAND SUTIRTO |  | 2023-04-12 | 2023-04-12 | 45 | Completed
5 | MODELLING WITH IMAGE AUGMENTATION | FREDERICK HUISAND SUTIRTO |  | 2023-04-12 | 2023-04-12 | 36 | Completed
6 | MODEL EVALUATION | FREDERICK HUISAND SUTIRTO |  | 2023-07-12 | 2023-07-12 | 15 | Completed
7 | ADD IMAGE PROCESSING | FREDERICK HUISAND SUTIRTO |  | 2023-07-12 | 2023-07-12 | 10 | Completed
8 | ADD MORE IMAGE PROCESSING | FREDERICK HUISAND SUTIRTO |  | 2023-07-12 | 2023-07-12 | 10 | Completed
9 | TEST MODEL PERFORMANCE | FREDERICK HUISAND SUTIRTO |  | 2023-07-12 | 2023-07-12 | 5 | Completed
10 | VISUALIZE MODEL ACC | FREDERICK HUISAND SUTIRTO |  | 2023-07-12 | 2023-07-12 | 10 | Completed
11 | DEPLOY | FREDERICK HUISAND SUTIRTO |  | 2023-09-12 | 2023-11-12 | 170 | Completed
12 | FRONTEND WEB | FREDERICK HUISAND SUTIRTO |  | 2023-11-12 | 2023-11-12 | 210 | Completed
13 | BACKEND WEB | FREDERICK HUISAND SUTIRTO |  | 2023-11-12 | 2023-11-12 | 140 | Completed
14 | TESTING WEB | FREDERICK HUISAND SUTIRTO |  | 2023-11-12 | 2023-11-12 | 45 | Completed